| # KAREEBERG # MUNICIPALITY | 2016/17 |
| --- | --- |

[IDP Process plan]

01 SEPTEMBER 2015

Table of Contents

INTRODUCTION	Error! Bookmark not defined.

SECTION 1	4

(a)	Process Plan	4

(b)	Institutional Arrangements	5

(c)	Establishment Process	6

(d)	Roles and Responsibilities	6

(i)	Mayor/Committee of Appointed Councillors	7

(ii)	The Municipality	7

(iii)	IDP Manager	7

(iv)	IDP Steering Committee	8

(v)	IDP Representative Forum	9

(vi)	Stakeholder and Community Representatives	10

(vii)	Provincial Government	11

(viii)	Support providers and planning professionals	11

(ix)	District Municipality	11

(e) 	Public Participation	12

(f)	    Process Programme	13

(g)	Process Timeframe	15

(h)	IDP Table of Contents	16

(i)          Provincial and National Plans	17

(j)	   Activity and Resource Plan	18

ACTIVITY AND RESOURCE PLAN BUDGET	19

SECTION 2	20

DISTRICT FRAMEWORK	20

DISTRICT FRAMEWORK PROCESS	20

DISTRICT FRAMEWORK CONTENTS	21

Binding National and Provincial Plans, Planning Requirements and Legislation	25

Amendment Procedures	25

TIMEFRAME FOR PREPARATION PROCESS	27

NATIONAL LEGISLATION APPLICABLE TO THE FUNCTIONS OF LOCAL GOVERNMENT	29

GENERAL MANAGEMENT	29

FINANCE	32

ADMINISTRATION/CORPORATE AND LEGAL SERVICES	33

HOUSING	33

TOWN PLANNING AND SPATIAL DEVELOPMENT	34

SAFETY AND SECURITY	34

HEALTH AND WELFARE	35

HUMAN RESOURCES	36

ELECTRICITY	37

ENVIRONMENT	37

ENGINEERING/TECHNICAL SERVICES	38

Introduction

Kareeberg Local Municipality has a constitutional mandate to deliver services to its communities.  The Integrated Development Plan (IDP) illustrates integrated strategic planning of the municipality.  The IDP framework outline legislative mandate of municipalities, a process plan, and identifies stakeholder’s roles and responsibilities, it outlines activities to be undertaken as well as sets times.

Section 28 of the Municipal Systems Act, Act 32 of 2000, requires that each Municipal Council adopts a process plan that would guide the planning, drafting, adoption and review of the IDP.  The process plan should have clear and established mechanisms, procedures and process to ensure proper consultation with the communities.  It should indicate clearly how the IDP process will work, who will be responsible for what, time frames and milestones will be set and a budget will be aligned to the programme.

From the above, it is clear that drafting an IDP requires a comprehensive planning process and the involvement of a wide range of role-players from inside and outside the Municipality.  Such a process has to be properly organised and prepared.  Therefore, the purpose of this document is to explain what a process plan is and to present a proposed process plan for the development of a new Integrated Development Plan for Kareeberg municipality.

# SECTION 1

(a)  PROCESS PLAN

A process plan functions as a business plan or management tool for each municipality which helps with the management of the IDP process on a day-to-day basis.  Its main objective is to stipulate what has to happen when, by whom, with whom, and where these things should be done in IDP preparation process.    In order to ensure that the Integrated Development Planning process complies with certain minimum quality standards and that proper co-ordination between and within the spheres of government is established, the preparation of the Process Plan is regulated by the Municipal Systems Act, 2000 as noted earlier.  In terms of section 28 of the Act, the following is required by the municipality:

28. (1) Each municipal council, within a prescribed period after the start of its elected term, must adopt a process set out in writing to guide the planning, drafting, adoption and review of its integrated development plan.  (2) The municipality must through appropriate mechanisms, processes and procedures established in terms of Chapter 4, consult the local community before adopting the process.  (3) A municipality must give notice to the local community of particulars of the process it intends to follow.  The Act further provides that the adopted process plan has to be submitted to the Provincial MEC responsible for Local Government on or before 31 March.  Thus it is on this basis that the following process plan has been drafted.

(b)  Institutional Arrangements

The elected Council is the ultimate decision-making forum on IDP’s.  The role of participatory democracy is to inform, negotiate and comment on those decisions, in the course of the planning process.

The following positions and structures are recommended and will serve as a guide:

- IDP Representative Forum

- Municipal Manager or IDP Manager

- IDP Steering Committee

- Project, Programme and Sectoral Task Teams

The IDP Manager, IDP Steering Committee and IDP Representative Forum are structures required throughout the Integrated Development Planning process.

The Project, Programme and Sectoral Task Teams will be small operational teams composed of a number of relevant municipal sector departments and technical officials involved in the management of the implementation and, where appropriate, community stakeholders directly affected by the project and programme.

Structure that manage/drive the IDP process

The following diagram is a schematic representation of the organizational structure that drives the IDP process.

MUNICIPAL COUNCIL

Mayor; or

Committee of appointed Councillors

Municipal Manager (IDP Manager)

IDP Steering Committee

IDP Representative Forum

Metropolitan

District and Local level

Subcommittees

Stakeholder Structures

Ward Committees

Ward Committees

Project, Programme & Sectoral Task Teams

Ward level

### (c) Establishment Process

- Committee of Appointed Councillors should, in consultation and with support of the Municipal Manager:

  - Define Terms of Reference for the IDP Manager and Steering Committee

  - Identify an appropriate IDP Manager, taking into consideration the importance of IDP

  - Assign responsibilities to the Municipal Manager regarding the drafting of the IDP;

  - Identify and nominate suitable candidates for the Steering Committee, ensuring that all relevant issues (e.g. LED, spatial, housing, finance etc.) have at least one responsible Senior Official; and

  - Include Portfolio Councillors where applicable.

- The newly established IDP Steering Committee should be responsible for the establishment of the IDP Representative Forum by:

  - Defining Terms of Reference and criteria for members of the IDP Representative Forum; and

  - Informing the public about the establishment of the IDP Representative Forum and request submission of applications from stakeholders/community groups indicating goals, objectives, activities, numbers of members, and constitution.

- IDP Steering Committee to:

- Establish subcommittees (if necessary) and decide on relationships/reporting mechanisms;

- Appoint the secretariat

(d) Roles and responsibilities

The roles and responsibilities of the proposed structure/stakeholders are as follows:

- Mayor / Committee of Appointed Councillors

- The Municipality

- IDP Manager

- IDP Steering Committee

- IDP Representative Forum

- Stakeholder and Community Representatives

- Provincial Government

- Support Providers and Planning Professionals

- District Municipality

# Roles and Responsibilities

## Mayor/Committee of Appointed Councillors

The Executive Committee or Executive Mayor of a Municipality or, if the Municipality does not have an Executive Committee or Executive Mayor, a committee of appointed councillors by the municipal council, must:

- Manage the drafting of the IDP;

- Assign responsibilities in this regard to the Municipal Manager; and

- Submit the draft plan to the municipal council for adoption.

These are structures already established and required by the Municipal Structures Act.  The Committee of Councillors appointed by the Municipal Council (the plenary type) in terms of Section 30 of the Systems Act, is a specific structure established for purposes of the IDP.  It is recommended that the responsibility for managing of the IDP be assigned to the Municipal Manager or IDP Manager on his behalf.

## The Municipality

- Prepare, decide and adopt a Process Plan.

- Undertake the overall management and co-ordination of the planning process, which includes ensuring that:

  - All relevant stakeholders are appropriately involved;

  - Appropriate mechanisms and procedures for public consultation and participation are applied;

  - The planning events are undertaken in accordance with the set timeframe;

  - The planning process is related to the Key Development Priorities in the Municipality; and

  - National and Provincial sector planning requirements are satisfied.

- Adopt and approve the IDP.

- Amend the IDP in accordance with the requirements of the MEC for Local Government.

- Ensure that the annual operational business plans and budget are linked to and based on the IDP.

## IDP Manager

The Municipal Manager or IDP Manager, on his behalf, is the responsible person for championing the Integrated Development Planning process.  The selection of the appropriate person is crucial for the success of Integrated Development Planning and has to be done as the first step towards preparing the Process Plan, since the IDP Manager is also the responsible person for designing the Process Plan.

The IDP Manager should be a dedicated person that has the required experience and authority to involve all relevant role players, and would have the following responsibilities:

- Responsible for the preparation of the Process Plan.

- Responsible for the day-to-day management of the planning process in terms of time, resources and people, and ensuring:

  - The involvement of all relevant role players, especially officials;

  - That the timeframes are being adhered to;

  - That the planning process is horizontally and vertically aligned and complies with national and provincial requirements;

  - That conditions for participation are provided; and

  - That outcomes are being documented

- Chairing the Steering Committee

- Management of consultants

## IDP Steering Committee

The Steering Committee should be a technical working team of dedicated Heads of Departments and Senior Officials who support the IDP Manager to ensure a smooth planning process.  The IDP Manager is responsible for the process, but will often delegate functions to members of the Steering Committee.  In Municipalities where relevant portfolio councillors want to be part of the IDP Steering Committee, they should be included.

- Composition of IDP Steering Committee:

- Chairperson 	-	Municipal Manager (or IDP Manager)

- Secretariat		-	Official of Municipality

- Members		-	Heads of Departments/Sectors and/or

- Senior officials of Municipality and/or Provincial Departments

Note:

Must also include:

- Financial Manager;

- Human Resource Manager;

- Corporate and Legal Manager;

- Marketing and Communications;

(2) The IDP Steering Committee will be responsible for the following:

- Provide terms of reference for subcommittees and the various planning activities.

- Commission research studies.

- Consider and comment on:

- Inputs from subcommittee(s), study teams and consultants, and

- Inputs from provincial sector departments and support providers (PIMS Centres, etc.)

- Process, summarise and draft outputs.

- Make recommendations.

- Prepare, facilitate and minute meetings.  Prepare and submit reports to the IDP Representative Forum.

Note:

- The IDP Steering Committee may establish subcommittees for specific activities and outputs which may include additional persons outside the Steering Committee.

- An official of the Municipality should be appointed to prepare, facilitate and document meetings.  The function should be the responsibility of the Municipal Planner or similar official.

- For the logistics of workshops, dissemination of information and invitations, the responsible official should be supported by an administrator.

## IDP Representative Forum

The IDP Representative Forum is the structure which institutionalises and guarantees representative participation in the Integrated Development Planning Process.  The selection of members to the IDP Representative Forum has to be based on criteria which ensure geographical and social representation.

- The IDP Representative Forum composition:

- Chairperson – A member of the Executive Committee or the Executive Mayor or a member of the Committee of Appointed Councillors

- Secretariat–IDP Steering Committee

- Members:

  - Members of the Executive Committee/Mayoral Committee;

  - Councillors (including Councillors who are members of the District Council and relevant Portfolio Councillors);

  - Traditional leaders;

  - Ward committee chairpersons;

  - Heads of Departments/Senior officials;

  - Stakeholder representatives of organised groups;

  - Stakeholder representatives of unorganised groups;

  - Resource persons; and

  - Community representative (e.g. RDP Forum)

Note:

- The preparation, facilitation and documentation of meetings and workshops of the IDP Representative Forum may need to be supported by professional planners, e.g. Shared Services Centres.

District Note:

- Similar structures will be required at District level for the District IDP;

- The composition of the District IDP Representative Forum should include Local Municipality representation

- IDP Representative Forum Chairpersons

- IDP Managers

(2) The Forum will be responsible to:

- Represent the interests of their constituents in the IDP process;

- Provide an organizational mechanism for discussion, negotiation and decision-making between the stakeholders and the Municipality;

- Ensure communication between all the stakeholder representatives; and

- Monitor the performance of the planning and implementation process.

(3) The IDP Representative Forum Code of Conduct

- The Code of Conduct will at least include the following:

- Meeting schedule (frequency and attendance);

- Agenda, facilitation and documentation of meetings;

- Purpose of the Forum;

- Regular feedback to constituents;

- Required majority of approval;

- Quorum requirements; and

- Resolution of disputes (including Provincial assistance)

## Stakeholder and Community Representatives

The Stakeholder and Community Representatives have the following roles and responsibilities to fulfill:

- Participating in the IDP Representative Forum to:

- Inform interest groups, communities and organizations on relevant planning activities and their outcomes;

- Analyze issues, determine priorities, negotiate and reach consensus;

- Participate in the designing of project proposals and/or the evaluation thereof;

- Discuss and comment on the draft IDP;

- Ensure that annual business plans and budgets are based on and linked to the IDP; and

- Monitor implementation performance of the IDP.

- Conducting meetings or workshops with groups, communities or organisations to prepare and follow-up on relevant planning activities.

Note:

The specific role of traditional leaders still needs further clarification.  The roles of the “civil society” are to be seen as an opportunity rather than a responsibility or duty.

## Provincial Government

The Provincial Local Government Department and Sector Departments have the following roles and responsibilities:

- Ensuring horizontal alignment of the Metropolitan and District Municipalities within the province;

- Ensuring vertical/sector alignment between provincial sector departments/provincial strategic plans and the IDP process at Metropolitan/District/Local level;

- Efficient financial management of provincial IDP grants;

- Monitoring the progress of the IDP processes;

- Facilitation of resolution of disputes related to IDP;

- Assist municipalities in the IDP drafting process when required;

- Facilitation of IDP – related training where required;

- Co-ordinate and manage the MEC’s assessment of IDPS;

- Provide relevant information on the provincial sector departments’ plans, programmes, budgets, objectives, strategies and projects in a concise and accessible manner;

- Provide sector expertise and technical knowledge to the formulation of municipal strategies and projects; and

- Engage in a process of alignment with Metropolitan and District Municipalities.

## Support providers and planning professionals

Support providers and professionals such as consultants, non-governmental organisations (NGO’s), Shared Services Centres and Municipal Planning officials have the following roles and responsibilities:

- Providing methodological/technical guidance to the IDP process;

- Facilitation of planning workshops;

- Documentation of outcomes of planning activities;

- Special studies or other product related contributions;

- Support to organized and unorganized groups and communities to more effectively engage in and contribute to the planning process; and to

- Ensure the IDP is aligned with the budget and planning requirements of provincial and national departments.

## District Municipality

- The District Municipality has the same roles and responsibilities as municipalities related to the preparation of a District IDP.

- Co-ordination roles regarding Local Municipalities:

- Ensuring horizontal alignment of the IDP’s of the local municipalities in the District Council area;

- Ensuring vertical alignment between district and local planning;

- Facilitation of vertical alignment of IDP’s with other spheres of government; and

- Preparation of joint strategy workshops with local municipalities, provincial and national role players.

### (e)  Public Participation

The structures, composition and positions may vary between different categories and types of Municipalities to suit the available human and institutional resources, but the proposed generic arrangements are recommended as a minimum requirement, and are based on the following principles:

- Public participation has to be institutionalised to ensure that all residents have an equal right to participate; and

- Structured participation must specify who is to participate, on behalf of whom, on which issues, through which organisational mechanisms and to what effect.

- Public participation is not equally relevant and appropriate in each stage of planning, and not all participation procedures are equally suitable for each planning step.  To limit participation costs, to avoid participation fatigue, and to optimise the impact of participation, the mechanisms of participation will have to differ from stage to stage.

PROPOSED PLANNING ACTIVITIES AND PUBLIC PARTICIPATION Phase 1: Analysis - Community and Ward Committee meetings organised by councillors - Stakeholders meetings - IDP Representative Forum Phase 2: Strategies - IDP Representative Forum and Steering committee meetings. - Public comments through advertisements. Phase 3: Projects - Municipality-wide Projects/Programmes - Technical subcommittees with few selected representatives of stakeholders organisations/civil society - IDP Representative Forum - Ward consultative meeting (s) Phase 4: Integration - Alignment Phase 5: Approval

### (f)Process Programme

The following is a proposed Integrated Development Planning Process that a Municipality will follow:

INTEGRATED DEVELOPMENT PLANNING PROCESS - IDP PLANNING PROCESS - Phase 1: Analysis - Legal Framework Analysis - Leadership Guidelines - Municipality Technical Development Analysis - Community and Stakeholder Development Analysis - Institutional Analysis - Economic Analysis - Socio-Economic Analysis - Spatial Analysis - Environmental Analysis - In-depth Analysis and identification of Key Development Priorities - Phase 2: Strategies - Identifying a Vision, Mission and Value System - Perform a Gap Analysis - Identify Key Performance Areas (KPA’s) - Determine Strategies and Development Objectives - Phase 3: Projects - Evaluation and Prioritisation of Projects and Programmes - Formulate Project and Programme Proposals in terms of: - KPA’s - Objectives and Key Performance Indicators (KPI’s) - Measures - Targets - Initiatives - Locations - Target Dates - Responsibility - Cost/Budget implications - Source of Finance - Compile Five Year Operational Business Plans which will include the identified Projects and Programmes - Phase 4: Integration - Screening, revision and integration of projects, programmes and Sectoral Operational business Plans - Institutional restructuring and alignment - Performance Management System - Compile an Integrated Communication Plan - Phase 5: Approval - Final approval by the Municipal Council - Advertisement - Public comments - ANNUAL IMPLEMENTATION - Compiling Operational Business Plan - Compiling Municipal Budget - Monitoring and Evaluation - Reporting

### (g)Process Timeframe ( 01/07/2016 – 30/06/2017)

(h) IDP Table of Contents

The following table of contents is proposed for the 2016/17 IDP of Kareeberg Municipality.

PROPOSED IDP TABLE OF CONTENTS - Introduction - Preparation Process - Process Plan - District Framework - Vision, Mission and Values - Existing Development Analysis - Legal Framework Analysis - Leadership guidelines - Technical Analysis (Basic facts, figures and Key Development Priorities - Summary of Community and Stakeholder Analysis (Key Development Priorities) - Institutional Analysis (Strengths and Weaknesses) - Economic Analysis (patterns, trends, opportunities and threats) - Socio-economic Analysis (poverty situations, gender issues, opportunity and threats) - Spatial Analysis (patterns, trends, opportunities and threats) - Environmental Analysis (trends, potential disasters, opportunities and threats) - In-depth Analysis and Identify Key Development Priorities - Development Strategies - Key Performance Areas - Strategies and Development Objectives - Summarised list of specific identified Development Projects, Programmes and Sector Plans - PROJECTS Project, Programme and Sector Plan Proposals (one page each) linked to Performance Management details - Institutional Organisational Structure - Committee system, community participation, decision-making process (all on diagram) - List of by-laws - Performance Management System including a list of Performance Based Contracts - Sector (departments) Five Year Operational Business Plans - Specific Plans/Frameworks - Communication Plan - Financial Plan (including capital) - Spatial Development Framework - Disaster Management Plan - Implementation Plan - Monitoring and Evaluation - Reporting

### (i) Provincial and National plans

The preparation and adoption of an Integrated Development Plan is undertaken within a broadly based legislative framework and plans.  The main plans and legislations that provide the foundation upon which an IDP rests may be summarized as follows:

PROVINCIAL AND NATIONAL PLANS/POLICIES - Water Services Development Plan; - Integrated Transport Plan; - Integrated Waste Management Plan; - Land Development Objectives (to be replaced by spatial planning as a requirement to be incorporated as a component in the IDP) - Housing strategies and targets; - Coastal management issues; - Local economic development strategies; - Integrated infrastructure planning; - Integrated energy planning; - Spatial framework - National Environmental Management Act principles; - Development Facilitation Act principles; - Environmental Implementation Plans; and - Environmental Management Plans

### Activity and Resource Plan

Considering the Proposed Integrated Development Planning Process (Process Programme) and that in terms of the Municipal Finance Management Act, Section 15 that prescribes that Municipalities must prepare draft budgets ready for discussion at the end of 31 March, the following Activity and Resource Plan is proposed:

| ACTIVITY AND RESOURCE PLAN |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Serial No | Planning Activity | Type of Event | Outputs | Planned dates | Responsibility |
| 1. 1.1 1.2 | PREPARATION – Commencement Date – 1 September 2015 Prepare a process plan for 2016/17 IDP Adoption of the process plan | Desk work Table the process plan to Council for adoption Advertise start of the IDP process | Completed draft process plan Council Resolution Input from stakeholders | 2 September 2015 30 Sept 2015 09 Oct 2015 | Mayor Municipal Manager LED/IDP Manager Shared Services LED/IDP Manager |
| 2. 2.1 (a) (b) (c) (d) (e) (f) (g) (h) (i) (j) | IDP PLANNING PROCESS PHASE 1: ANALYSIS Community & Stakeholder Development Analysis Municipal Technical Development Analysis Institutional Analysis Economic Analysis Socio-Economic Analysis Spatial Analysis Environmental Analysis Legal Framework Analysis Leadership Guidelines In-depth Analysis | Desk work (compilation of a situational analysis report in preparation for determining the Council’s strategic priorities, vision and development objectives) Engagements with political structures, sector departments and other stakeholders Steering Committee IDP Rep Forum Community consultative meeting(s) | Status Quo Report and public participation | 01/10 Oct – 30 Nov 2015 12-16 Oct 2015 20 Oct 2015 09 Nov 2015 10-13 Nov 2015 | LED/IDP Manager Shared Services |
|  | Phase 1: |  |  |  |  |
| 2.2 (a) (b) (c) | PHASE 2: STRATEGIES Vision, Mission & Values Gap Analysis and KPA’s Strategies & Development Objectives | Revision of priority issues, municipal strategies, KPA’s and gap analysis in the current IDP Develop the measurable objectives for the next financial year and include the required budget for achieving those objectives | Determined /reviewed priority issues and strategic objectives for service delivery for the next financial year | 16-2 0 Nov 2015 | LED/IDP Manager Shared Services District PMS Officer |
|  | Phase 2: |  |  |  |  |
| 2.3 (a) (b) (c) | PHASE 3: PROJECTS Identify Development Project Formulate Project & Programme Proposals Sector Operational Business Plans | Identification and prioritization of IDP projects from priority issues Submission of projects by sector departments | Projects for implementation in the next financial year identified | 18-22 Jan 2016 | LED/IDP Manager HODs Members of IDP Rep Forum Members of Steering committee Ward Councillors |
|  | Phase 3: |  |  |  |  |
| 2.4 (a) (b) | PHASE 4: INTEGRATION Screening, revision & integration of projects and programmes Institutional restructuring( Summary & inclusion of available sector plans) IDP Rep Forum Community consultative meetings Steering Committee Draft IDP as a working document | Sector departments alignment Information requested from officials Confirmation of priority issues Revised projects Sector departments alignment Revision of priority issues Integration between Budget and IDP Work on Draft IDP to be tabled to Council | Alignment of MTSFs, MTEFs, programmes and budgets Received information from sector departments Confirmed priority issues Revised projects and alignment of IDP to national and provincial programmes/issues Integration between budget and IDP Input from stakeholders IDP and budget alignment Draft IDP | 25-29 Jan 2016 01-12Feb 2016 15 Feb 2016 17-19 Feb 2016 22 Feb – 04 March 2016 07-27 March 2016 | All Managers Community LED /IDP Manager Shared Services CFO |
|  | Phase 4: |  |  |  |  |
| 2.5 (a) (b) (c) (d) | PHASE 5: APPROVAL Approval, including submission to the MEC and Advertisement Submit adopted Draft IDP to MEC for Local Government Steering Committee meeting Admin and political outreaches Final 2016/2017 IDP and budget drafts Submit IDP and budget to MEC for Local Government SDBIP and PMS | Table draft IDP and concept budget to Council for adoption Submit and publish adopted IDP and budget for comments MEC to comment on Draft IDP Discussion of the Draft IDP Report back from IDP projects and Budget allocation Discussion of SDBIP IDP and Budget discussion Table final IDP and budget to Council for approval IDP and Budget to be submitted to MEC for Local Government Table to Council Submit SDBIP to Mayor for approval 28 days after the approval of the budget The approved SDBIP’s and performance agreements are submitted to MEC and are advertised within 14 days after approval | Adopted IDP and Council Resolution Copies of advertisements Received MEC’s comments Consideration of public and MEC’s Comments Legal compliance Received reports on IDP projects and resource allocation SDBIP IDP and Budget Adopted IDP and Budget Legal compliance Legal compliance Approved, signed SDBIP by the Mayor Compliance Copies of Advertisements | 31March 2016 11 April 2016 08 April 2016 02 May 2016 06 May 2016 09-13 May 2016 16-17 May 2016 31 May 2016 09 June 2016 14 June 2016 28 June 2016 11 July 2016 | Mayor MM LED/IDP Manager CFO LED/IDP Manager All Managers Community LED /IDP Manager Shared Services CFO Municipal Manager LED/IDP Manager PMS Officer |

# ACTIVITY AND RESOURCE PLAN BUDGET The costs of the IDP process have to be budgeted for by the Municipality. This budget serves as a basis for applying for financial contributions from Provincial and National levels. It can also help the municipal management to monitor whether the planning costs are reasonable in relation to other budget items. In case the planning costs seem to be unacceptably high, one will have to reconsider the Process Plan in order to devise a less costly process, or additional contributions must be obtained from other sources.

CONCLUSION

The above table list of deliverables leads to the activities that will be undertaken whilst reviewing the current IDP for Kareeberg Municipality.  This process plan as being part of the IDP review preparation phase ensures that the role players within the process ahead are well prepared.  All activities outlined within this document have been prepared in close interrelation with the Framework that governs both the District and Local Municipalities.

# SECTION 2

# DISTRICT FRAMEWORK

The District Framework binds both the District Municipality and the Local Municipalities in the area, and is supposed to ensure proper consultation, co-ordination and alignment of the planning process of the District Municipality and the various Local Municipalities.

Each District Council must, in consultation with its Local Municipalities, adopt a District Framework for Integrated Development Planning in the area as a whole.  The District Framework must be developed during a joint workshop, and is binding on both District and Local Municipalities.

A District Municipality must conduct its own Integrated Development Planning in “close consultation with the Local Municipalities in that area.”  This District IDP must be aligned with the District Framework and the IDP processes.  Proposals of local Municipalities must be “taken into account” in the drafting process.

## DISTRICT FRAMEWORK PROCESS District briefing session of IDP Managers regarding: - IDP Planning Process and approach - Legislation (Municipal Structures and Systems Act) - Support Systems (shared Services Centres, etc) All Municipalities draft tentative programmes with alignment needs District to arrange the workshop and to compile a listof National and Provincial binding legislation and planning requirements. District Framework workshop to: - Co-ordinate the individual programmes and agree on the Framework Programme; - Discuss and agree on alignment needs and mechanisms; and - Develop and agree on legally binding legislation and relevant planning requirements Adoption of Framework by District Municipality. Framework to be considered and adopted by all Local Municipalities within the District boundaries.

# DISTRICT FRAMEWORK CONTENTS

The following is a proposed Table of Contents, with due consideration to prescriptions contained in legislation:

- Introduction

- Consultation Procedures

- Matters requiring alignment

- Binding National and Provincial Plans, Planning Requirements and Legislation

- Amendment Procedures

## Introduction

The following will at least be addressed:

- Purpose of the Framework

- Role players:

- District Municipality

- Local Councils

- Provincial and National Government

## Consultation Procedures

### Role players

It is proposed that the following persons and structures be involved in the alignment process:

Between Kareeberg municipality and the District Municipality:

- District:  IDP Manager and Chairperson of the IDP Representative Forum

- Local Council:  IDP Manager and Chairperson of the IDP Representative Forum;

- Shared Services Centre; and

- Provincial IDP Co-ordinator

Between District/Local Municipalities and Provincial/National Government

- District IDP Manager;

- Local IDP Manager;

- Provincial IDP Co-ordinator

- Provincial/National Senior Sector Department Officials; and

- Senior Officials of relevant Service Providers (Eskom, Water Board, Telkom, etc.)

The following Alignment Process is proposed:

- District IDP Steering Committee to present alignment needs at District Framework workshop.

- At workshop:

- Compile joint list of alignment needs and discuss mechanisms to ensure alignment;

- Agree on alignment mechanism, as well as timeframes and role players to be involved; and

  - Agree on a final decision mechanism to dissolve disputes or differences between Local Municipalities and between Local and District Municipalities.

- District Municipalities to engage (meeting, written communication) with Provincial and National Departments and other stakeholders to outline District alignment needs and expectations and agree on mechanisms.

- Each municipality (local and district) to consider alignment when devising their Process Plans (Process Programme with timeframe).

### Management Alignment Structure

The following Alignment Structure is proposed:

DISTRICT IDP REPRESENTATIVE FORUM - Chairperson District IDP Representative Forum Chairperson - Members - Local IDP Representative Forum Chairpersons - District IDP Manager - Local IDP Managers - Shared Services Centre and/or Provincial Co-ordinator

### Consultation during Planning Process

The proposed process for consultation between the District Municipality and the Local Municipalities during the 1 Year Planning Process is as follows:

- Phase 1:  Analysis

District Municipality may perform analysis related to region-wide issues and co-ordinate and align Key Development Priorities with the Local Municipalities.

- Phase 2:  Strategies

Local Municipalities should be invited to District strategy workshops to jointly discuss the most appropriate problem-solving strategies.  Provincial and National specialists and competent resource-persons from civil society could be invited to join this process, which will be facilitated by staff of the District-level PIMS Centre.

- Phase 3:  Projects

Project and Programme planning will require co-ordination and alignment between the District and Local Municipalities.

- Phase 4:  Integration

During this phase Local and District Municipalities will consolidate the project proposals in order to finalise their respective integrated Development plans and programmes.

- Phase 5:  Approval

The District will play an important role in horizontal (cross-border issues) and vertical co-ordination.

Local and District-level planning will be done parallel, but inform each other mutually, rather than in a one-sided bottom-up or top-down manner.

| DISTRICT ALIGNMENT ACTIVITY PROGRAMME |  |  |  |
| --- | --- | --- | --- |
| Phases | Alignment Activity | Local Municipality | Local Government/ Provincial/National |
| Phase 1: Analysis | Key Development Priorities | X | X |
| Phase 2: Strategies | District-level Strategy workshop | X | X |
| Phase 3: Projects | Project planning co-ordination | X | X |
| Phase 4: Integration | Integration of Sector Programme (Provincial/National) | X | X |
| Phase 5: Approval | - Submission of draft IDP - Comment on draft IDP - Compiling District-level Summary of local IDPs | X X X | X X |

MODEL FOR ALIGNMENT

Phase 1 Analysis

Phase 2 Strategies

Phase 3 Projects

Phase 4 Integration

Phase 5 Approval

Provincial

DISTRICT

Regional issues         Regional Projects					       Approved by

District

Draft District IDP			Council

Horizontal and vertical

LOCAL

Co-ordination &

Integration

Local issues				Local projects	Draft Local IDP		Approved by

Local Council

### Matters requiring alignment

Matters that may require alignment may include the Integrated Development Planning process (5 phases), as well as Section 84 (1) and (2) of the Municipal Systems Act, 2000 (The Division of Powers).

LIST OF MATTERS THAT MAY NEED ALIGNMENT THROUGHOUT THE DISTRICT - IDP Process Programmes - IDP Process Timeframes - IDP Table of Contents - Five Year Planning Process - Phase 1: Analysis (Co-ordinate Key Development Priorities) - Phase 2: Strategies - Phase 3: Projects - Phase 4: Integration - Phase 5: Approval (Requires horizontal and vertical alignment - Annual implementation - Municipal Budgets - Monitoring and Evaluation - Reporting - Section 84 (1) and (2) The Division of Powers - Electricity and gas reticulation - Fire-fighting services - Local tourism - Municipal airports - Municipal planning (IDP) - Municipal public transport - Municipal public works - Municipal health services - Water and sanitation services - Potable water supply systems - Domestic waste-water - Sewage disposal systems - Cemeteries, funeral parlours and crematoria - Markets - Municipal abattoirs - Municipal roads - Refuse removal, refuse dumps and solid waste disposal

### Binding National and Provincial Plans, Planning Requirements and Legislation

Provincial legislation will differ from one Province to another.  It is important that Provincial plans and Legislative guidelines be assessed and listed as part of the District Framework.

- District Municipalities, with the support of the Provincial IDP Co-ordinator must prepare a list of Provincial legislation and other important national and provincial information for the Framework workshop.

- At the workshop, the District Municipalities must provide the above-mentioned list and familiarise the Local Municipalities with the content thereof.

The following is an example of a list of Provincial and National Sectoral Plans, Programmes and Policies:

Sector Plans, Programmes, Policies and Frameworks - Water Services Development Plan; - Integrated Transport Plan; - Integrated Waste Management Plan; - Land Development Objectives (to be replaced by spatial planning as a requirement to be incorporated as a component in the IDP) - Housing strategies and targets; - Coastal management issues; - Local economic development strategies; - Integrated infrastructure planning; - Integrated energy planning; - Spatial framework; - National Environmental Management Act principles; - Development Facilitation Act principles; - Environmental implementation Plans; and - Environmental Management Plans

A list of National Legislation applicable to the functions of Local Government is attached as Annexure “C”

### Amendment Procedures

Proposed principles and procedures for monitoring of the Process Plan, and the amendment of the District Framework are as follows:

- Each Municipality will be responsible for monitoring its own Process Plan and ensure that the District Framework is being followed as agreed.

- Proposed procedures for deviations:

  - Establish a committee of IDP Managers that meet after each phase to jointly assess progress and decide on amendments;

  - Each local Municipality must inform the District Municipality of deviations  from the Action Programme that affect District-wide activities (e.g. the identification of municipal priority issues is delayed and the District-wide strategy workshop has to be postponed);

  - The District Municipality has the mandate to decide when and how an amendment takes place, and therefore postpones, an activity or continues with the agreed programme; or

  - All the relevant Municipalities have to agree before the Framework is amended.

### TIMEFRAME FOR PREPARATION PROCESS

DISTRICT FRAMEWORK

IDP Managers co-ordination and preparation for workshop

- District

- Local

- Provincial

District Framework

Workshop

Adoption of District Framework by the District Council

Co-ordinated at

District Level

Local and			Local and District Councils

District Councils

PROCESS PLAN

Executive Committee/Mayoral Committee Meeting:

Nomination of IDP Manager

Establishment of IDP Steering Committee

IDP Steering Committee Meeting:

Decision on roles & responsibilities

Identification of stakeholders, role players

Advertisement

Terms of reference for IDP Representative Forum

Draft Action Programme with Timeframe

IDP Steering Committee Meeting:

Detailed Process Programme with timeframe & resources

Mechanisms & procedures for:

Public Participation and Alignment

Give notice to the Public

Municipal Council Meeting:

Adaption of Process Plan:

Institutional arrangements

Roles & Responsibilities

IDP Representative Forum

Timeframe

Mechanisms for alignment and public participation

Provincial & national binding legislation

Budget

Metropolitan

Drafted by all 								Councils

Municipalities

Proposal for the IDP Representative Forum Members Report to Municipal Council for Consideration

1st Week			2nd Week				3rd Week				4th Week

TIMEFRAME	______________________________________________________________________________________________________________

Proposed Co-ordination Process

MUNICIPAL COUNCIL IDP STEERING COMMITTEE Co-ordinate total process Draft: - Process Plan - District Framework (if applicable) - Planning Phases 1 – 5 - Final IDP - All reports and recommendations Facilitate, prepare and minute meetings and workshops, including the IDP Representative Forum Prepare reports to council: - Process Plan - IDP per phase - Final IDP Mayoral Committee or Executive Committee or Committee of Appointed Councillors IDP Representative Forum

# NATIONAL LEGISLATION APPLICABLE TO THE FUNCTIONS OF LOCAL GOVERNMENT

## GENERAL MANAGEMENT

| NATIONAL LEGISLATION | SUMMARY/SCOPE OF LEGISLATION |
| --- | --- |
| Constitution of the Republic of South Africa 1996 | To introduce a new constitution for the Republic of South Africa and to provide for matters incidental thereto |
| Local Government: Municipal Systems Act, 2000 | - To give effect to “developmental local government” - To set principles, mechanisms and processes to promote social and economic upliftment of communities and to ensure access to affordable services for all - To set a framework for planning, performance management ,resource mobilisation and organisational change and community participation |
| Local Government: Municipal Structures Act, 1998 | - To provide for the establishment of municipalities in accordance with the requirements relating to the categories and types of municipality, the division of functions and powers between municipalities and appropriate electoral systems - To regulate internal systems, structures and office-bearers |
| Consumer Affairs (Unfair Business Practices) Act, 1996 | - To provide for the investigation, prohibition and control of unfair business practices in the interest of consumers |
| Local Government Cross-boundary Municipalities Act, 2000 | - To authorise the establishment of cross-boundary municipalities, to provide for the re-determination of the boundaries of such municipalities under certain circumstances and to provide for matters connected therewith |
| Local Government: Municipal Demarcation Act, 1998 | - To provide for the demarcation of boundaries of municipalities for the establishment of new municipalities |
| Municipal Electoral Act, 2000 | - To regulate municipal elections - To amend certain laws - To provide for matters connected therewith |
| Organised Local Government Act, 1997 | - To provide for the recognition of national and provincial organisations representing the different categories of municipalities and the designation of representatives to participate in the National Council of Provinces etc. |
| Promotion of Local Government Affairs Act, 1983 | - To provide for the co-ordination of functions of general interest to local authorities and of those functions of local authorities which should in the national interest be co-ordinated |
| Local Government Transition Act, 1993 REPEALED EXCEPT FINANCIAL PROVISIONS | - To provide for matters relating to municipalities in the interim phase, powers and functions of municipalities and actions of officials and councillors |
| Occupational Health and Safety Act, 1993 | - To provide for occupational health and safety in the work place and the protection of persons outside the work place against hazards to health and safety arising from activities of persons at the work place |
| Promotion of Access to Information Act, 2000 | - To control and regulate the right of all persons to access to information |
| Promotion of Fair Administrative Justice Act, 2000 | - To give effect to the right to administrative action that is lawful, reasonable and procedurally fair in terms of the Constitution of the Republic of South Africa 1996 |
| Promotion of Equality & Prevention of Unfair Discrimination Act, 2000 | - To give effect to section 9 read with item 23(1) of Schedule 6 to the Constitution of the Republic of South Africa, 1996, to prevent and prohibit unfair discrimination and harassment - To promote equality and to eliminate unfair discrimination & to prevent & prohibit hate speech & to provide for matters connected therewith |

### FINANCE

| NATIONAL LEGISLATION | SUMMARY/SCOPE OF LEGISLATION |
| --- | --- |
| Business Act, 1991 | - To repeal certain laws regarding the licensing of businesses - To provide for the licensing and operation of certain businesses, shop hours and related matters |
| Debt Collectors Act, 1998 | - To provide for controlled debt collecting |
| Income Tax Act, 1962 | - To provide for the payment of taxes on incomes of persons and taxes on donations |
| Insolvency Act, 1936 | - To consolidate and amend the law relating to insolvent persons and their estates |
| Local Authorities Capital Development Fund Ordinance, 1978 READ WITH Local Government Affairs Second Amendment Act, 1993 | - To provide for the establishment and management of a Capital Development Fund and for matters incidental thereto |
| Municipal Accountants’ Act, 1988 | - To provide for the establishment of a Board for Municipal Accountants and for the registration of Municipal Accountants and the control of their profession |
| Municipal Consolidated Loans Fund Ordinance, 1952 READ WITH Local Government Affairs Second Amendment Act, 1993 | - To provide for the establishment and management of a Consolidated Loans Fund as approved by the Premier |
| Municipal Finance Management Act, 2003 | - To regulate financial management in the local sphere of government to require that all revenue, expenditure assets and liabilities of municipalities and municipal entities are managed efficiently and effectively, to determine responsibilities of persons entrusted with local sphere financial management and to determine certain conditions and to provide for matters connect therewith |
| Pension Benefits for Councillors of Local Authorities Act, 1987 | - To provide the pension benefits for councillors |
| Public Financial Management Act, 1999 | - To regulate financial management in the national and provincial governments and, inter alia, provincial public entities |
| Prescribed Rate of Interest Act, 1975 | - To prescribe and regulate the levying of interest from debtors |
| Reporting by Public Entities Act, 1992 | - To provide for the reporting to Parliament by public entities |
| Value-added Tax Act, 1991 | - To provide for the taxation in respect of the supply of goods and services |
| Local Government Transition Act, 1993 REPEALED EXCEPT FINANCIAL PROVISIONS | - To provide for matters relating to municipalities in the interim phase, powers and functions of municipalities and actions of officials and councillors |
| Local Government: Property Rates Act | - To regulate general property valuation |

### ADMINISTRATION/CORPORATE AND LEGAL SERVICES

| NATIONAL LEGISLATION | SUMMARY/SCOPE OF LEGISLATION |
| --- | --- |
| Electoral Act, 1998 | - To manage and regulate on national, provincial and local government level |
| Expropriation Act, 1975 | - To provide for the expropriation of land and other property for public and certain other purposes and matters connected thereto |

### HOUSING

| NATIONAL LEGISLATION | SUMMARY/SCOPE OF LEGISLATION |
| --- | --- |
| Housing Arrangements Act, 1993 | - To provide for the establishment of a national and regional Housing Board(s) and the abolition of certain existing boards |
| Rental Housing Act, 1999 | - To define the responsibility of Government in respect of rental housing |
| Residential Landlord and Tenant Act, 1997 | - To provide for the regulation of landlord-tenant relations in order to promote stability in the residential rental sector in the province |

### TOWN PLANNING AND SPATIAL DEVELOPMENT

| NATIONAL LEGISLATION | SUMMARY/SCOPE OF LEGISLATION |
| --- | --- |
| Provision of Certain Land for Settlement, 1993 | - To provide for the designation of certain land and to regulate the subdivision of such land and settlement of persons thereon |
| Advertising on Roads & Ribbon Development Act, 1940 | - To control advertising on national and regional roads |
| Black Communities Development Act, 1984 | - To control the land use rights within the former black areas |
| Development Facilitation Act, 1995 | - To provide for Integrated Development Plans, reflecting current planning and to institutionalise development tribunals for evaluating applications |
| Physical Planning Act, 1991 | - To provide guidelines for the drafting of urban development plans |
| Regulations on Advertisements on or Visible from National Roads, 1998 | - To control all advertising on national and regional roads |
| Subdivision of Agricultural Land Act, 1970 | - To control the subdivision of farm land and agricultural holdings |
| Town and Regional Planners Act, 1984 | - To provide for the training and registration of professional Town Planners |

### SAFETY AND SECURITY

| NATIONAL LEGISLATION | SUMMARY/SCOPE OF LEGISLATION |
| --- | --- |
| Criminal Procedure Act, 1977 | - To consolidate and regulate procedure and evidence in criminal proceedings |
| Disaster Management Bill, 2000 | - To provide for an integrated, co-ordinated and common approach to disaster management by all spheres of government and related matters |
| Fire Brigade Services Act, 1987 | - To provide for the rendering of fire brigade services and certain conditions to the rendering of the service |
| Gatherings and Demonstration Act, 1993 | - To control public gatherings and procession of marches |
| Hazardous Substances Act, 1973 | - To control matters relating to gas, petrol and liquids |
| National Land Transport Bill, 1999 |  |
| National Land Transport Interim Arrangements Act, 1998 | - To make arrangements relevant to transport planning and public road transport services |
| Urban Transport Act, 1977, as amended 1992 | - To promote the planning and provision of adequate urban transport facilities |
| National Road Traffic Act, 1996 | - To regulate traffic on public roads, the registration and licensing of motor vehicles and drivers, including fitness requirements and incidental matters |
| Road Traffic Management Corporation Act, 1999 | - To provide in the public interest for co-operative and co-ordinated strategic planning, regulation, facilitation and law enforcement in respect of road traffic matters and to provide for matters connected therewith |
| Prevention of Illegal Eviction from and Unlawful Occupation of Land Act, 1998 | - To provide for the eviction of unlawful occupants of land and the protection of the rights of such occupants under certain conditions |
| South African Police Service Act, 1995 | - To provide, inter alia, for a municipal (city) police |

### HEALTH AND WELFARE

| NATIONAL LEGISLATION | SUMMARY/SCOPE OF LEGISLATION |
| --- | --- |
| Hazardous Substances Act, 1973 | - To control matters relating to gas, petrol and liquids |
| Health Act, 1977 | - To provide for the promotion of the health of the inhabitants of the Republic - To render health services - To define the duties, powers and responsibilities of certain authorities which render such services - To co-ordinate such services |
| National Policy for Health Act, 1990 | - To provide for control measures to promote the health of the inhabitants of the Republic and for matters connected thereto |

### HUMAN RESOURCES

| NATIONAL LEGISLATION | SUMMARY/SCOPE OF LEGISLATION |
| --- | --- |
| Employment Equity Act, 1998 | - To promote the constitutional right of equality and the exercise of true democracy - To eliminate unfair discrimination in employment - To redress the effect of unfair discrimination in the work place - To achieve a workforce representative of the population |
| Basic Conditions of Employment Act, 1997 | - To give effect to the right to fair labour practice - To provide for the regulation of basic conditions of employment |
| Compensation of Occupational Injuries and Diseases Act, 1993 | - To regulate the categories of persons entitled to compensation for occupational injuries and diseases, and to determine the degree of disabled employees |
| Labour Relations Act, 1995 | - To regulate the organisational rights of trade unions, the right to strike and lock-outs - To promote and facilitate collective bargaining and employee participation in decision-making - To provide simple procedures for labour disputes |
| Skills Development Act, 1998 | - To provide for the implementation of strategies to develop and improve the skills of the South African workforce - To provide for learnerships, the regulation of employment services and the financing of skills development |
| Skills Development Levies Act, 1999 | - To provide for the imposition of a skills development levy and for matters connected therewith |
| South African Qualifications Authority Act, 1995 | - To provide for the establishment of a National Qualifications Framework and the registration of National Standards Bodies and Standards Generating Bodies and the financing thereof |
| Unemployment Insurance Act, 1966 | - To provide for the payment of benefits to certain persons and the dependants of certain deceased persons - To provide for the combating of unemployment |

ELECTRICITY

| NATIONAL LEGISLATION | SUMMARY/SCOPE OF LEGISLATION |
| --- | --- |
| Electricity Act, 1987 | - To provide for and regulate the supply of electricity and matters connected thereto |

### ENVIRONMENT

| NATIONAL LEGISLATION | SUMMARY/SCOPE OF LEGISLATION |
| --- | --- |
| Environmental Conservation Act, 1982 | - To provide for environmental impact assessments and exemptions, noise control areas etc. |
| Environmental Conservation Act, 1989 | - To provide for the effective protection and controlled utilisation of the environment and for matters incidental thereto |
| National Environmental Management Act, 1998 | - To provide for co-operative environmental governance by establishing principles for decision-making on matters affecting the environment and to provide for matters connected thereto |

### ENGINEERING/TECHNICAL SERVICES

| NATIONAL LEGISLATION | SUMMARY/SCOPE OF LEGISLATION |
| --- | --- |
| Advertising on Roads & Ribbon Development Act, 1940 | - To control advertising on national and regional roads |
| Regulations on Advertisements on or visible from national roads, 1998 | - To control all advertising on national and regional roads |
| National Building Regulations and Building Standards Act, 1977 | - To provide for the promotion of uniformity in the law relating to the erection of buildings in the areas of jurisdiction of local authorities and for the prescribing of building standards |
| National Water Act, 1998 | - To provide for fundamental reform of the laws relating to water resources |
| Water Services Act, 1997 | - To provide for the rights of access to basic water supply and sanitation, national standards and norms for tariffs and services development plans |