## Monthly Report
Monthly Report (DoRA) (Non-financial)
(only registered MIG projects)
| Name of Municipality : |  | Kareeberg Municipality
| Date Submitted : |  | 28-06-2013
Municipality | Ward No /Area / Village | National Project Number | MIS Form ID | Project Name (incl sub-place) | MIG Component (B,P or E) | Project Category (e.g. water, santitation, PMU etc) | New/Rehabilitate | Bulk Project (yes / no) | Internal Reticulation (Yes / No) | Rural / Urban | EPWP (Yes / No) | Planned Households, km's (as in MIG 1 form) | Project start date | Project Status (Registered/Design/Tender/Construction(e.g. Construction 25%) / Completed) | Total Project Cost | Registered MIG Funds | Counter Funding | Budgeted MIG Funds (2011-2012) | Total Actual Expenditure on Previous Allocations (incl 2010/11,2011/12) | Total Actual Expenditure in the 2012-2013 financial year on MIG funds | Monthly Expenditure
Kareeberg | 3 | MIG/NC0358/R,ST/11/13 | 195946: | Vosburg: Streets and Storm Water | B | Roads | New |  |  | Rural | No | 960 m | April 2012 | Construction | 6211606 | 6211606 | 0 | 6211606 | 1809944.7 | 2220431.08 | 1669561.78
Kareeberg | 2 | MIG/NC0359/R,ST/10/13 | 1068: | Carnarvon Streets & Stormwater | B | Roads | New |  |  | Rural | No | 1644 m | Desember 2011 | Construction | 10870313 | 10870313 | 0 |  | 2323809.18 | 4866985.55 | 2179144.15
Kareeberg | 4 | MIG/NC0357/R,ST/11/13 | 1082: | Van Wyksvlei Streets & Stormwater | B | Roads | New |  |  | Rural | No | 330 m | April 2012 | Construction | 6729239 | 6729239 | 0 |  | 1022780.09 | 1286449.37 | 1286449.37
Kareeberg | Carnarvon | MIG/NC0466/CC12/13 | 213172 | MIG 1235: Kareeberg Carnarvon: High Mast Lighting | B | High mast Lighting | New |  |  | Rural | No |  | June 2013 | Completed | 1200134 | 1200134 | 0 |  | 0 | 1200134 | 1200134
[20 empty] | 9574000 | 6335289.3
SIGNED BY MUNICIPAL MANAGER (Or delegated person, include letter of delegation) | [11 empty] | 2934
NAME: |  | W. de Bruin
SIGNATURE:
DATE: |  | 28-06-2013
CONTACT DETAILS: |  | 053 382 3012
CHIEF FINANCIAL OFFICER
NAME: |  | P.B. Rossouw
SIGNATURE:
DATE: |  | 28-06-2013
CONTACT DETAILS: |  | 053 382 3012
Note on A7: : name of implemeting agent
Note on B7: : project location
Note on C7: : As appearing on the project approval letter.
Note on E7: : Same as in the MIG 1 form and approval letter.
Note on G7: : Water, sanitation, roads & stormwater, sports facilities, community lighting, solid waste disposal sites, cemeteries, libraries, parks & open spaces community facilities
Note on M7: : Indicate households for water, sanitation, sports facilities, community lighting, solid waste disposal sites, other community facilities. Indicate km's for roads & stormwater projects
Note on N7: : Date when constractor commenced work
Note on O7: : Registered, design, tender, construction (can give %), completed
Note on S7: : Amount committed to be spent in the current financial year.

## Completed projects
COMPLETED PROJECTS
Municipality | Ward/Area/Village) | National Project Number | Project Name | MIG Component (B,P or E) | Project Category (e.g. water, santitation, PMU etc) | New/Rehabilitate | Bulk Project (yes / no) | Internal Reticulation (Yes / No) | Rural / Urban | Labour Intensive/ EPWP (Yes / No) | Planned Households (as in MIG 1 form) | Project Status | Project start date | Project completion date | Total Project Cost | Registered MIG Funds | Counter Funding | Total Actual Expenditure in the 2012-2013 financial year on MIG funds | Total Actual Expenditure on the project | Comments
Kareeberg | Carnarvon | MIG/NC0466/CC12/13 | Mig 1235: Kareeberg Carnarvon: High Mast Lighting | B | Street Lighting | New |  | No | Rural | No |  | Completed | June 2013 | June 2013 | 1200134 | 1200134 | 0 | 1200134 | 1200134
Completed
Completed
Completed
Completed
Completed
SIGNED BY MUNICIPAL MANAGER (Or delegated person, include letter of delegation)
NAME: |  | W de Bruin
SIGNATURE:
DATE: |  | 28-06-2013
CONTACT DETAILS: |  | 053-382 3012
CHIEF FINANCIAL OFFICER
NAME: |  | P.B. Rossouw
SIGNATURE:
DATE: |  | 28-06-2012
CONTACT DETAILS: |  | 053-382 3013