## Monthly Report
Monthly Report (DoRA) (Non-financial)
(only registered MIG projects)
Name of Municipality :
Date Submitted :
Municipality | Ward No /Area / Village | National Project Number | MIS Form ID | Project Name (incl sub-place) | MIG Component (B,P or E) | Project Category (e.g. water, santitation, PMU etc) | New/Rehabilitate | Bulk Project (yes / no) | Internal Reticulation (Yes / No) | Rural / Urban | EPWP (Yes / No) | Planned Households, km's (as in MIG 1 form) | Project start date | Project Status (Registered/Design/Tender/Construction(e.g. Construction 25%) / Completed) | Total Project Cost | Registered MIG Funds | Counter Funding | Budgeted MIG Funds (2011-2012) | Total Actual Expenditure on Previous Allocations (incl 2010/11,2011/12 and 2012/13) | Total Actual Expenditure in the 2012-2013 financial year on MIG funds | Monthly Expenditure
Kareeberg | 3 | MIG/NC0358/R,ST/11/13 | 195946: | Vosburg: Streets and Storm Water | B | Roads | New |  |  | Rural | No | 467 m | April 2012 | Construction | 6211606 | 6211606 |  | 6211606 | 1809944.7 | Nil | Nil
Kareeberg | 2 | MIG/NC0359/R,ST/10/13 | 1068: | Carnarvon Streets & Stormwater | B | Roads | New |  |  | Rural | No | 650 m | Desember 2011 | Construction | 10870313 | 10870313 |  |  | 2323809.18 | Nil | Nil
Kareeberg | 4 | MIG/NC0357/R,ST/11/13 | 1082: | Van Wyksvlei Streets & Stormwater | B | Roads | New |  |  | Rural | No | 772 m | April 2012 | Construction | 6729239 | 6729239 |  |  | 1022780.09 | Nil | Nil
[20 empty] | 0 | 0
SIGNED BY MUNICIPAL MANAGER (Or delegated person, include letter of delegation)
NAME: |  | A.P.F. van Schalkwyk
SIGNATURE:
DATE: |  | 31-08-2012
CONTACT DETAILS: |  | 053 382 3012
CHIEF FINANCIAL OFFICER
NAME: |  | P.B. Rossouw
SIGNATURE:
DATE: |  | 31-08-2012
CONTACT DETAILS: |  | 053 382 3012
Note on A7: : name of implemeting agent
Note on B7: : project location
Note on C7: : As appearing on the project approval letter.
Note on E7: : Same as in the MIG 1 form and approval letter.
Note on G7: : Water, sanitation, roads & stormwater, sports facilities, community lighting, solid waste disposal sites, cemeteries, libraries, parks & open spaces community facilities
Note on M7: : Indicate households for water, sanitation, sports facilities, community lighting, solid waste disposal sites, other community facilities. Indicate km's for roads & stormwater projects
Note on N7: : Date when constractor commenced work
Note on O7: : Registered, design, tender, construction (can give %), completed
Note on S7: : Amount committed to be spent in the current financial year.

## Completed projects
COMPLETED PROJECTS
Municipality | Ward/Area/Village) | National Project Number | Project Name | MIG Component (B,P or E) | Project Category (e.g. water, santitation, PMU etc) | New/Rehabilitate | Bulk Project (yes / no) | Internal Reticulation (Yes / No) | Rural / Urban | Labour Intensive/ EPWP (Yes / No) | Planned Households (as in MIG 1 form) | Project Status | Project start date | Project completion date | Total Project Cost | Registered MIG Funds | Counter Funding | Total Actual Expenditure in the 2010-2011 financial year on MIG funds | Total Actual Expenditure on the project | Comments
Completed
Completed
Completed
Completed
Completed
Completed
Completed
SIGNED BY MUNICIPAL MANAGER (Or delegated person, include letter of delegation)
NAME: |  | A.P.F. van Schalkwyk
SIGNATURE:
DATE: |  | 31-08-2012
CONTACT DETAILS: |  | 053-382 3012
CHIEF FINANCIAL OFFICER
NAME: |  | P.B. Rossouw
SIGNATURE:
DATE: |  | 31-08-2012
CONTACT DETAILS: |  | 053-382 3012