## Water
QUARTERLY NON FINANCIAL (KPI) REPORT FOR JUNE 2011
WATER SECTOR
[6 empty] | BACKLOGS: HOUSEHOLDS SERVED WHEN PROJECT IS COMPLETED |  | FINANCIAL |  | PLANNED OUTPUTS IN MIG 1
[8 empty] | Project cost (MIG) | Exp at end of March 2010 as on the New DORA | WATER BASELINE INFORMATION
Municipality | Ward | National Project Number | Project Name (incl. Sub-Place) | MIG Component (B,P or E) | Project Status(registered, Tender&Design, construction, completed, retention | Planned | Households served |  |  | Number of boreholes | Number of reservoirs | Number of water treatment plants | Number of pump stations | Number of raw water storage dams | Kilometres of supply lines | Number of stand pipes reticulated | Number of metered stand pipes reticulated | Number of water meters reticulated | Kilometres of pipe line reticulated
Note on G20: palesa: we rae currently awaiting for Budget maintanence approval for water work
Note on G21: palesa: we are currently constructing a resevoir for storage and the are stands without connections and astan meter and pipe

## Sanitation
QUARTERLY NON FINANCIAL (KPI) REPORT FOR JUNE 2011
SANITATION
[6 empty] | BACKLOGS : HOUSEHOLDS SERVED WHEN PROJECT IS COMPLETED |  | FINANCIAL |  |  | PLANNED OUTPUTS ON MIG 1
[8 empty] | Project Cost (MIG) | Exp at end of March 2011 as on new DORA | SANITATION
Municipality | Ward | National Project Number | Project Name (incl. Sub-Place) | MIG Component (B,P or E) | Project Status(registered, Tender&Design, construction, completed, retention | Planned | Households served |  |  | Number of treatment works | Number of oxidation ponds | Number of pump stations | Kilometres of main outflow lines | Number of Waterborne Systems | Number of VIP's
1
Note on D15: OEM: technical report - clarify with Mitta
Note on D51: OEM: technical report - clarify with Mitta
Note on G44: palesa: THIS DOES NOT INCLUDE NEW AREA eg Mooiplaats, Mooidraai

## Roads
QUARTERLY NON FINANCIAL (KPI) REPORT FOR March 2013
ROADS AND STORMWATER
[6 empty] | BACKLOGS: KM |  | FINANCIAL |  | ROADS OUTPUTS | [9 empty] | SIDEWALKS OUTPUTS |  |  | STORMWATER OUTPUTS
Municipality | Ward | National Project Number | Project Name (incl. Sub-Place) | MIG Component (B,P or E) | Project Status(registered, Tender&Design, construction, completed, retention |  |  | Project cost (MIG) | Exp at end of March 2013 as on New Dora | Kilometres of all-weather engineered gravel roads constructed | Kilometres of block paved roads constructed | Kilometres of tarred roads constructed | Kilometres of gravel access collectors | Kilometres of block paved access collectors | Kilometres of tarred access collectors | Number of drains installed | Kilometres of guard rails installed | No of road signs installed | Number of Low Level Bridges Constructed | Kilometres of gravel sidewalks | Kilometres of block paved sidewalks | Kilometres of tarred sidewalks | Kilometres of channels | Kilometres of pipelines | Number of retention ponds
[6 empty] | Planned | KM constructed
Kareeberg | 2 | MIG/NC0359/R,ST/10/13 | 195914: Carnarvon: Streets and Storm Water | P | Completed |  |  | 6985004.24 | 2520113.69 |  | 1420
Kareeberg | 3 | MIG/NC0358/R,ST/11/13 | 195946: Vosburg: Streets and Storm Water | P | Registered |  |  | 6211606 | 233570.04
Kareeberg | 4 | MIG/NC0357/R,ST/11/13 | 196445: Van Wyksvlei: Streets and Storm Water | P | Registered |  |  | 6729239
Note on D52: OEM: technical report - clarify with Mitta
Note on L7: Totaal 1644 Materiaal aangekoop
Note on L8: Aankoop van materiaal

## Sports & Recreat.
QUARTERLY NON FINANCIAL (KPI) REPORT FOR JUNE 2011
SPORT AND RECREATION
[6 empty] | BACKLOGS: HOUSEHOLDS SERVED WHEN PROJECT IS COMPLETED |  | FINANCIAL |  | SPORTS & RECREATION OUTPUTS
Municipality | Ward | National Project Number | Project Name (incl. Sub-Place) | MIG Component (B,P or E) | Project Status(registered, Tender&Design, construction, completed, retention | Backlogs Eradicated |  | Project cost (MIG) | Exp at end of March 2011 as on New DORA | Number of Multi purposes sport centre / fields | Number of Parks and open spaces | Number of Beaches and amusement facilities
[6 empty] | Planned | Households served

## DTI
QUARTERLY NON FINANCIAL (KPI) REPORT FOR JUNE 2011
DTI
[6 empty] | BACKLOGS: HOUSEHOLDS SERVED WHEN PROJECT IS COMPLETED |  | FINANICIAL |  | MICRO-ENTERPRISE OUTPUTS
Municipality | Ward | National Project Number | Project Name (incl. Sub-Place) | MIG Component (B,P or E) | Project Status(registered, Tender&Design, construction, completed, retention |  |  | Project cost (MIG) | Exp at end of March 2011 as on new dora | Number of Local Trading Stals (municipal assets) | Number of Local Market Stals (municipal assets) | Number of Other Amenities (municipal assets)
[6 empty] | Planned | Households served

## Distaster Mngmnt
QUARTERLY NON FINANCIAL (KPI) REPORT FOR JUNE 2011
DISASTER MANAGEMENT
[6 empty] | BACKLOGS: HOUSEHOLDS SERVED WHEN PROJECT IS COMPLETED |  | FINANICIAL |  | DISASTER OUTPUTS
Municipality | Ward | National Project Number | Project Name (incl. Sub-Place) | MIG Component (B,P or E) | Project Status(registered, Tender&Design, construction, completed, retention | Backlogs Eradicated |  | Project cost (MIG) | Exp at end of March 2011 as on new dora | Number of Disaster Management Centres Constructed
[6 empty] | PLANNED | Households served

## Solid Waste
QUARTERLY NON FINANCIAL (KPI) REPORT FOR JUNE 2011
SOLID WASTE
[6 empty] | BACKLOGS: HOUSEHOLDS SERVED HWEN PROJECT S COMPLETED |  | FINANCIAL |  | SOLID WASTE
Municipality | Ward | National Project Number | Project Name (incl. Sub-Place) | MIG Component (B,P or E) | Project Status(registered, Tender&Design, construction, completed, retention | Backlogs Eradicated |  | Project cost (MIG) | Exp at end of March 2011 as on new dora | Number of licensed solid waste removal sites | Number of refuse transfer stations
[6 empty] | Planned | Households served

## Comm Lighting
QUARTERLY NON FINANCIAL (KPI) REPORT FOR JUNE 2011
[6 empty] | BACKLOGS: HOUSEHOLDS SERVED WHEN PROJECT IS COMPLETED |  | FINANCIAL |  | Community Lighting
Municipality | Ward | National Project Number | Project Name (incl. Sub-Place) | MIG Component (B,P or E) | Project Status(registered, Tender&Design, construction, completed, retention | Backlogs Eradicated |  | Project cost (MIG) | Exp at end of March 2011 as on new DORA | Number of high masts | Number of street lights
[6 empty] | Planned | Households served

## General
QUARTERLY NON FINANCIAL (KPI) REPORT FOR JUNE 2011
OTHER INFRASTRUCTURE
[6 empty] | BACKLOGS: HOUSEHOLDS SERVED WHEN PROJECT IS COMPLETED |  | FINANCIAL |  | GENERAL
Municipality | Ward | National Project Number | Project Name (incl. Sub-Place) | MIG Component (B,P or E) | Project Status(registered, Tender&Design, construction, completed, retention |  |  | Project cost (MIG) | Exp at end of March 2011 | Number of Thusong Centres | Number of Community halls | Number of Child care facilities / Nurseries | Number of Cemeteries / Crematoriums | Number of Facilities for animals | Kilometres of Fencing of Cemeteries | Number of Municipal Abattoirs | Number of Libraries | Number of Municipal parking areas / facilities | Number of Bus shelters | Number of Taxi ranks
[6 empty] | Planned | Households served

## Employment
QUARTERLY NON FINANCIAL (KPI) REPORT FOR JUNE 2011
EMPLOYMENT (projects on construction and completed) labour from April 2010 accumulative until March 2011
[7 empty] | PERSONS | [5 empty] | PERSON DAYS
Municipality | Ward | National Project Number | Project Name (incl. Sub-Place) | MIG Component (B,P or E) | Project Category | Project Status(registered, Tender&Design, construction, completed, retention | Women | Men | Youth (Male) | Youth (Female) | Disabled (Male) | Disabled (Female) | Women | Men | Youth (Male) | Youth (Female) | Disabled (Male) | Disabled (Female)
Note on D37: OEM: technical report - clarify with Mitta
Note on D136: OEM: technical report - clarify with Mitta
Note on D137: OEM: technical report - clarify with Mitta

## Empowerment
|  |  | QUARTERLY NON FINANCIAL KPI REPORT SEPTEMBER 2011 |  | EMPOWERMENT
ECONOMIC EMPOWERMENT from April 2010 until March 2011
Municipality | Project number | National Project Number | Project Name (incl. Sub-Place) | MIG Component (B,P or E) | Number of SMME Utilised | Expenditure on SMME | Number of BEEs Utilised | Expenditure on BEEs
Note on C37: OEM: technical report - clarify with Mitta
Note on C136: OEM: technical report - clarify with Mitta
Note on C137: OEM: technical report - clarify with Mitta